## Sheet1
252.5
Meeting #0 - Zadani projektu | 1 | 2011-10-07
Studium .net MVC, rozdily oproti WebForms | 1 | 2011-10-08
Studium NuGet, Scaffolding, testing project | 3.5 | 2011-10-09
Use case, Domain model, wireframe prototype | 3 | 2011-10-12
use case, prototype, meeting #1 | 1 | 2011-10-14
Zalozeni Git repositare | 0.25 | 2011-10-16
Studium .net MVC - connection, Entity Framework, Unity | 2 | 2011-10-19
Design model | 4 | 2011-10-19
Design model | 1 | 2011-10-20
Studium Google Authentication, Google Groups api | 0.5 | 2011-10-20
Meeting #2 - struktura projektu, datove vrstvy, EF connection | 1.5 | 2011-10-21
Studium EntityFramework inheritance | 0.5 | 2011-10-29
Zalozeni projektu, zaklad Data, Business | 1.5 | 2011-10-29
Solved EF run errors, QuestionManager base, Question View | 1.5 | 2011-10-30
Finished data layer model, learning Controllers & Views, basic Form functionality | 4.5 | 2011-10-31
Forms grid and basic functionality, UnitTests, ConnectionStrings, sql, css basics, BaseController, HtmlExtender | 7 | 2011-11-03
Meeting #3 - Unity injection | 2 | 2011-11-04
Exploring capabilities of jQuery UI, MVC AJAX and custom validation | 0.5 | 2011-11-05
Unity injection - database config from web.config | 1 | 2011-11-05
Learning Memberships in .net, MVC Url routing; implementing Authorization | 4 | 2011-11-08
Learning MembershipProvider etc, FormsAuthentication, MVC Controls; Implementing Authorization | 4 | 2011-11-09
Authentication, User management, Little styles, Components | 5.5 | 2011-11-10
Authentication implementing | 2 | 2011-11-15
User creating and deleting | 1 | 2011-11-17
User password and IsActive flag, Form permissions | 2 | 2011-11-18
Questions base | 2 | 2011-11-19
Creating and editing Questions | 7.25 | 2011-11-24
Styles, Database project | 3.5 | 2011-11-30
Form creating, question types implementation, FormInstance creating, styles | 5.5 | 2011-12-01
Small improvements (cropping form name, …) | 0.5 | 2011-12-07
Editing Choice question, FormInstance generation and view, new window for filling | 6 | 2011-12-08
Meeting - Implementing Multiline and MultipleChoice questions in Form edit view | 1 | 2011-12-09
User form filling | 5 | 2011-12-15
Meeting - Implementing Students listing | 2 | 2011-12-16
TopButtons implementation and styles | 3 | 2011-12-26
Researching Moodle and Studentova Berlicka | 2 | 2011-12-27
Debug version of icons with implementation | 1 | 2011-12-27
Form editing - implementation, javascript, styles | 6 | 2011-12-28
Form filling - implementation, javascript, styles | 6 | 2011-01-03
Writing final report and related LaTeX learning | 5 | 2011-01-04
Writing final report, preparing presentation | 10 | 2011-01-05
Setting up database project, writing what to do, overview | 3 | 2012-02-16
Scale question gui and controls | 4 | 2012-02-18
Scale question, showing filled tests list and window | 7 | 2012-02-19
Showing filled tests list and window | 2.5 | 2012-02-21
Refactoring, groups | 3 | 2012-02-27
Groups | 5 | 2012-02-29
Groups, Permissions & Managers refactoring | 5 | 2012-03-04
Groups, TrainingTest javascript | 5 | 2012-03-05
TrainingTest javascript & styles | 1.5 | 2012-03-06
Stavy formularu | 2 | 2012-03-08
Znamkovani, ManagersContainer + refactoring manageru, added some permissions | 7 | 2012-03-10
MultipleChoiceAnswer saving, ChoiceItems constrains, nahled testu, | 6 | 2012-03-11
Cas na vyplneni - core, javascript, styles | 3 | 2012-03-13
Cas na vyplneni - zmeneno na sekundy | 1.5 | 2012-03-15
Maximalni pocet vyplneni, mazani otazky, mazani alternativni otazky, skupiny pri editaci formu, styly, michani choice odpovedi | 6 | 2012-03-18
Google services studium, Google Groups csv import, vlastni obsluha vyjimek | 5 | 2012-03-19
Overovani prav na urovni Controller Actions, studium moznosti exportu do Google Docs | 2.5 | 2012-03-20
Michani Choice items, Lokalizace | 2 | 2012-03-24
Lokalizace, styly, Export do Google Docs | 5 | 2012-03-25
Export do CSV, Google Docs | 2 | 2012-03-27
FillFormReport, Export do CSV a Google Docs | 8 | 2012-03-31
Zjistovani moznosti Wiki (.net, JS), Skripta - DB, modely atd, Integrace Wiki .NET parser | 8 | 2012-04-01
Integrace MarkItUp | 2 | 2012-04-02
Editace skript | 2 | 2012-04-03
Rozchození LaTeX template, příprava a studium materiálů pro rešerši, osnova | 6 | 2012-04-05
Finalizace UseCase, Domain a Class diagramů, řešení LaTeX obrázků, referenci, češtiny, psaní bakalářky - osnova, uvod, popis | 10 | 2012-04-07
Psaní - rešerše + screenshoty, řešení vlastních enumerací | 4 | 2012-04-08
Psaní - bezpečnost, řešení citací, řešení a tvorba příkazů pro vkládání zdrojového kódu C# | 7 | 2012-04-09
Psaní - formulare, otazky, role, prava, ...; reseni tabulek, obrazku | 6 | 2012-04-10