## Sheet1
57.75
Meeting #0 - Zadani projektu | 1 | 2011-10-07
Studium .net MVC, rozdily oproti WebForms | 1 | 2011-10-08
Studium NuGet, Scaffolding, testing project | 3.5 | 2011-10-09
Use case, Domain model, wireframe prototype | 3 | 2011-10-12
use case, prototype, meeting #1 | 1 | 2011-10-14
Zalozeni Git repositare | 0.25 | 2011-10-16
Studium .net MVC - connection, Entity Framework, Unity | 2 | 2011-10-19
Design model | 4 | 2011-10-19
Design model | 1 | 2011-10-20
Studium Google Authentication, Google Groups api | 0.5 | 2011-10-20
Meeting #2 - struktura projektu, datove vrstvy, EF connection | 1.5 | 2011-10-21
Studium EntityFramework inheritance | 0.5 | 2011-10-29
Zalozeni projektu, zaklad Data, Business | 1.5 | 2011-10-29
Solved EF run errors, QuestionManager base, Question View | 1.5 | 2011-10-30
Finished data layer model, learning Controllers & Views, basic Form functionality | 4.5 | 2011-10-31
Forms grid and basic functionality, UnitTests, ConnectionStrings, sql, css basics, BaseController, HtmlExtender | 7 | 2011-11-03
Meeting #3 - Unity injection | 2 | 2011-11-04
Exploring capabilities of jQuery UI, MVC AJAX and custom validation | 0.5 | 2011-11-05
Unity injection - database config from web.config | 1 | 2011-11-05
Learning Memberships in .net, MVC Url routing; implementing Authorization | 4 | 2011-11-08
Learning MembershipProvider etc, FormsAuthentication, MVC Controls; Implementing Authorization | 4 | 2011-11-09
Authentication, User management, Little styles, Components | 5.5 | 2011-11-10
Authentication implementing | 2 | 2011-11-15
User creating and deleting | 1 | 2011-11-17
User password and IsActive flag, Form permissions | 2 | 2011-11-18
Questions base | 2 | 2011-11-19